# Vora Addis Hotel – Hotel Management System Implementation Plan

22 October 2026 · Prepared by Dagmawi

## Overview

A single web-based system can run Vora Addis's rooms, restaurant, bar, café, laundry and billing in about 5 months, delivered in four phases with the front desk live by month 3.

Vora Addis is a 3-star hotel on Jomo Kenyatta Street in Kirkos, Addis Ababa, a 15-minute walk from the ECA Conference Center and Meskel Square. It lists five room types, free breakfast, a restaurant, bar, café, laundry/dry cleaning, parking and a daily manager's reception, and it sells through online travel agencies such as Expedia.

Goals of the system:

- One guest folio: room, restaurant, bar, café and laundry charges all land on the guest's bill

- No double bookings between walk-ins, phone bookings and OTAs

- Real-time room status shared by front desk and housekeeping

- ERCA-compliant invoicing in ETB, with USD for foreign guests

- Daily owner reports: occupancy, ADR, RevPAR, revenue by outlet

Room count, staff numbers and current tools are not public yet; they are listed as open questions at the end.

## Scope: modules

Ten modules, split into must-have for go-live and later additions.

| Module | What it does | Users | Phase |
| --- | --- | --- | --- |
| Reservations | Calendar, rate plans, deposits, group and corporate bookings, cancellations | Front desk, sales | 1 |
| Front desk | Check-in/out, room assignment, guest registration, passport scan, key handover | Receptionists | 1 |
| Guest folio & billing | One bill per stay, split bills, deposits, refunds, ETB/USD | Front desk, cashier | 1 |
| Housekeeping | Room status (dirty, clean, inspected, out of order), task lists, mobile view | Housekeepers, supervisor | 2 |
| Restaurant, bar & café POS | Orders, kitchen tickets, post to room, breakfast tracking | Waiters, cashier | 2 |
| Laundry & dry cleaning | Item intake, pricing, post to room | Laundry staff | 2 |
| Inventory & purchasing | Stock for kitchen, bar, minibar, amenities; supplier orders | Store keeper | 3 |
| Reports & dashboard | Occupancy, ADR, RevPAR, outlet sales, night audit, cashier shift close | Manager, owner | 1–3 |
| Channel manager & booking engine | Sync availability and rates with Expedia/Booking.com; direct bookings on the hotel website | Revenue manager | 3 |
| Staff, roles & audit log | Users, permissions per role, who changed what | Admin | 1 |

Out of scope for v1: payroll and full accounting (export to the hotel's accounting software instead), door-lock integration, and a guest mobile app.

## Ethiopia-specific requirements

These are what make a local system worth more than an imported PMS; confirm each with the hotel's finance team and accountant.

- Tax invoicing: VAT and service charge on every bill, TIN on invoices, and a plan for the Ministry of Revenues' fiscal device / e-invoicing rules (confirm the current requirement before build)

- Currencies: ETB as base, USD price display and payment for foreign guests, daily exchange rate entered by finance

- Payments: cash, card (POS terminal), Telebirr, CBE Birr and bank transfer, each tracked per cashier shift

- Guest registration: nationality, passport or Kebele/Fayda ID, visa details, and a printable guest register for police checks

- Language: English and Amharic interface for staff; guest invoices in English

- Connectivity: an offline mode for the POS and front desk, syncing when the internet returns, plus a local backup

- Calendar: Gregorian by default, Ethiopian date shown on invoices if the hotel wants it

## Architecture and tech stack

One cloud-hosted backend serves every screen, so a bar tab posted to room 204 shows on the front desk instantly.

| Layer | Components |
| --- | --- |
| Clients | Front desk (web): check-in, billing · POS tablets: restaurant, bar, café · Housekeeping app: phones, room status · Manager dashboard: reports, night audit |
| Backend API (NestJS or Django REST) | Reservations · Folio and billing · POS · Housekeeping · Laundry · Inventory · Reports · Auth and audit · Offline sync queue · VAT and service charge rules |
| Data | PostgreSQL main database · nightly off-site backup · Redis for sessions and queues |
| Integrations | Channel manager (Expedia, Booking.com) · Telebirr, CBE Birr, card terminals · SMS and email confirmations · fiscal receipt printer |

| Layer | Suggested choice | Why |
| --- | --- | --- |
| Frontend | React (Next.js) + PWA | Works on desktops and cheap Android tablets; installable, offline cache |
| Backend | NestJS (TypeScript) or Django REST | Fast to build, strong typing / admin tools |
| Database | PostgreSQL | Reliable for money and bookings; transactions prevent double booking |
| Hosting | AWS (Cape Town region) or a local data centre | Low latency; AWS student credits help early costs |
| Auth | Role-based access, PIN login for POS staff | Fast at the till, safe for managers |

## Data model

The Folio is the centre: every outlet posts charges to it, and it becomes the invoice.

| Entity | Key fields | Links to |
| --- | --- | --- |
| Guest | name, phone, email, nationality, ID/passport no., visa | Reservations, Folios |
| RoomType | name, capacity, base rate | Rooms, RatePlans |
| Room | number, floor, status, housekeeping status | RoomType |
| RatePlan | name, season, price ETB/USD, breakfast included | RoomType |
| Reservation | dates, source (walk-in, phone, OTA, direct), status, deposit | Guest, RoomType, Room |
| Stay | actual check-in/out, room moves | Reservation, Folio |
| Folio | balance, currency, status | Stay, Charges, Payments |
| Charge | outlet, item, qty, amount, VAT, service charge | Folio, Order, LaundryTicket |
| Payment | method, amount, currency, reference, cashier shift | Folio |
| Order (POS) | outlet, table/room, items, waiter | Charge, MenuItem |
| LaundryTicket | items, price, status | Charge |
| HousekeepingTask | room, type, assignee, done at | Room, Staff |
| InventoryItem | unit, stock, reorder level | PurchaseOrder, MenuItem recipe |
| Staff / Role | name, role, permissions | AuditLog |
| AuditLog | who, what, when, before/after | all |

## Roadmap

Front desk goes live in week 11, the full system by week 22. Every phase ends with a demo to the manager and a written sign-off before the next starts.

| Phase | Weeks | Deliverables | Gate at end |
| --- | --- | --- | --- |
| 0. Discovery | 1–3 | Site visit, interviews, requirements, screen designs, tax invoice check | Scope signed |
| 1. Front office | 4–11 | Reservations, check-in and out, guest folio and billing, roles and audit log | Front desk live |
| 2. Outlets | 12–16 | Housekeeping app, restaurant and bar POS, laundry, offline sync | Full hotel go-live |
| 3. Growth | 17–22 | Inventory, channel manager, booking engine, owner dashboard | Handover |

## Team, budget and rollout

A team of 4–5 can deliver this; the budget below is a placeholder to replace with your own rates.

| Role | Count | Focus |
| --- | --- | --- |
| Project lead / BA | 1 | Requirements, hotel liaison, testing sign-off |
| Backend developer | 1–2 | API, database, tax and billing logic |
| Frontend developer | 1 | Front desk, POS and dashboard screens |
| UI/QA (part-time) | 1 | Design, test cases, training material |

Running costs to quote the hotel: cloud hosting (one small server + managed database + backups), domain and SSL, SMS/email credits, and an annual support contract. Hardware the hotel may need: receipt printers, a kitchen printer, a passport scanner and tablets for housekeeping.

Pricing models to offer: a one-time build fee plus monthly support, or a monthly subscription (SaaS) that you can later resell to other Addis hotels.

Go-live steps:

- Load rooms, rates, menus, staff and future bookings from the current system

- Train each department on its own screens (half a day each)

- Run in parallel with the old process for one week

- Switch over on a low-occupancy day, with a developer on site for the first 3 nights

- Hand over admin guide and a support line with agreed response times

## Risks and open questions

| Risk | Mitigation |
| --- | --- |
| Internet or power outages stop sales | Offline-first POS and front desk; UPS for the server room |
| Tax rules change or are misread | Confirm invoice format with the hotel's accountant before Phase 1 ends |
| Staff resist a new system | Train by department; keep screens simple; Amharic labels |
| OTA double bookings during switch-over | Close OTA inventory for go-live day, then sync |
| Scope keeps growing | Fix Phase 1 scope in writing; new requests go to a later phase |

Questions to ask Vora Addis before quoting:

- How many rooms, and how many of each room type?

- What do they use today (paper, Excel, another PMS)?

- Which OTAs do they sell on besides Expedia?

- Do they have a fiscal printer, and which model?

- How many staff per department, and how many shifts?

- Is there an accounting system the folio data must export to?

- Budget range and target go-live date?

## Sources

Vora Addis Hotel – Expedia